|  |  |
| --- | --- |
| Your Company Name  ESTIMATE / 01-01-2013 | Your Address  City, State Zip |

|  |  |
| --- | --- |
| **Client Name**  Address  City, State Zip | **ESTIMATED COST**  $XXXX.00 |

Introduction

Use this space to introduce what the estimate is for.

|  |  |  |  |
| --- | --- | --- | --- |
| Item Description | Estimated Time | Estimated Cost | Resourses Associated |
| DB - ER - Tables | ½ days | … | Senior DBA |
| DB - ER – Views | ½ days | … | Senior DBA |
| DB - ER - Relationship | 1 days | … | Senior DBA |
| DB – Logic Schema – Attributes | 3 days | … | 2 Junior + Senior Review(DBA) |
| DB – Logic Schema – Keys | 1 days |  | 2 Junior + Senior Review(DBA) |
| DB – Physical – Tables | 1 days |  | DBA |
| DB – Physical – View | 1 days |  | DBA |
| DB – Physical – Relations | ½ days |  | Auto Generation: 2 Junior + Senior Review(DBA) |
| DB – Physical – Data | 1+1/2 days |  | Junior |
| Front End – Master Page | 5 days |  | 2 Senior |
| Front End – Base Style | 5 days |  | Web Designer |
| Front End – External Components – Dependencies | 1 days |  | 2 Junior |
| Front End – External Components - Integration | 2 days |  | 2 Junior |
| Front End – Data Integration | 3 days |  | Senior(Architect) |
| Back End – Data Interface – Table | 2 days |  | Senior(Architect 50%) + DBA(50%) |
| Back End – Data Interface – View | 2 days |  | Senior(Architect 50%) + DBA(50%) |
| Back End – Data - ORM | 1 days |  | Auto-generation (Junior) |
| Back End – Controller – Data – Interface | 2 days |  | Senior(Architect 50%) + 2 Junior |
| Back End – Controller – Data Structures | 1 days |  | Senior Dev(50%) |
| Back End – Business Logic – Insert Appointment | 3 days |  | 2 Junior(33% each) + Senior(33%) |
| Back End – Business Logic – Remove Appointment | 3 days |  | 2 Junior(33% each) + Senior(33%) |
| Back End – Business Logic – Move Appointment | 3 days |  | 2 Junior(33% each) + Senior(33%) |
| Testing – Testing DB | 4 days |  | Tester |
| Testing – Milestone | 5 days |  | Tester |
| Packaging | 2 days |  | Packager |
| Documentation & Manual Review | 5 days |  | DBA – Web Designer - Senior |
|  | TOTAL | $0.00 |  |

Terms & Conditions

Use this space to specify what your client is agreeing to when accepting the estimate.

It’s smart to request an up-front deposit for any large project.

Signatures

|  |  |  |  |
| --- | --- | --- | --- |
| Your Name | Date | Client’s Name | Date |